## Timeline_Lumbung Building
TIMELINE FOR THE LUMBUNG BUILDING
2020
| JUN |  |  |  |  | JULY |  |  |  | AUG |  |  |  |  | SEPT |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  |  | REMARKS | PIC
ACTIVITIES | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
A. LUMBUNG KICK-off
1. Kick-off Gathering
2.1. [First Meeting] Introduction to the kick-off agenda |  | 10 | [29 empty] | 1/ First meeting for everyone to meet everyone. And a kick-off to start to get to know each other. 2/ Will need a 2nd day to continue the kick-off.
2.2. [Second Meeting] Getting to know each other: conversation in duo's and triangles | [31 empty] | 1/ In duo's or triangle to start knowing about partners, Artistic Team will join in each group to only play role as harvester. 2/ Make sure all recorded well, so if we need: we can always return back to the audio/video recording. 3/ Verena and Erby talk with Martin to divide the zoom into three zooming room and make sure they're all recorded.
2.3. Reflection, define the next steps together | [31 empty] | Come to a conclusion with all Lumbung Partners about how we continue further. Create a proposal for next steps and form a small hosting team that will work with few of Artistic Team on planning of coming three months (then rotate). Discuss harvesting and involvement of students to join the process as well.
2. Follow-up Process
2.1. First Hosting Team (Artistic Team + Lumbung Partners) start to work together, planning for the first 3 months and rotating after. |  |  | 15 | [18 empty] | 31 | [9 empty] | Contacting diverse type of "schools" in the network to join the process as harvester. The idea is to maybe have young curators, students, artists etc. linked to lumbung partners do this, or build a relation with f.e. Gudskul, Raw Material, 32 degrees East and De Appel for this. | Hosting Team
2.2. Continue to converse among smaller group to map resources, to discuss more in triangle formart, etc |  |  | 15-29 | [28 empty] | Creative harvesters from each partner should participate to join the process. Make sure all the harvests be returned back to the whole group. | Hosting Team
2.3 Informal duo and triangle talks
2.4. Host a session to reflect on the harvest of the triangle |  |  |  |  | 29-5 | [26 empty] | Collective sessions to discuss the documenta lumbung (school / economy). | Hosting Team, Artistic Team
2.5. Preparation for the self-hosted/regular programming sessions |  |  |  |  | 29-5 | [26 empty] | Who will be most ready to start with? If necessary: budget will start to be included for translation purposes, etc. | Hosting Team, Artistic Team
2.6. Start to map the communication possibilities |  |  |  |  | 29-5 | [26 empty] | Working closely with lumbung partners: communication / art mediation working group should join the preparation process to be able to make a plan. Further: the hosting team should share the harvest to communication WG. | Hosting Team, Comm Team
2.7. Collective knowledge sessions hosted by the different partners | [5 empty] | 6 | [15 empty] | 31 | [9 empty] | The time where a broader ecosystem be joining in this school process. In between: will also be filled with other sharing knowledge sessions with topics that will enrich. Need to be aware of summer holidays. | Hosting Team, Artistic Team
2.8. To develop and execute communication plan | [5 empty] | 6 | [15 empty] | 31 | [9 empty] | Proceed by the communication working group, to be included within further mediation / communication plan, art mediation working group should join. Lumbung partners could produce something with their own communication network/platform too. | Hosting Team, Comm Team
2.9. Mapping possibilities of translation | [5 empty] | 6 | [15 empty] | 31 | [9 empty] | The closer people of the Artistic team to each initiative start talking about this with Lumbung Partners. Projection of budget should be prepared and shared. Collective fundraising process could be started. | Artistic Team, Hosting Team